## Slide 1
NATA FOUNDATION
Free Communications Program
Process Guide
A reference for abstract submission, review, and program scheduling

## Slide 2
ANNUAL PROCESS TIMELINE
Committee Setup & Abstract Submission
AUG – NOV
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
August
FC Chair confirms the committee roster for the upcoming year (13 members, plus the Research Committee Chair & Convention Planning Committee Representative)
  Potential new members are discussed at the January meeting; FC Chair contacts them as needed
FC Chair works with NATA Foundation staff to review and update the call for abstracts for the website
September
Call for abstracts is posted on the website by early September
FC Chair confirms all incoming committee members
Online abstract submission opens in mid- to late-September
October
FC Chair and NATA Foundation staff schedule the January meeting
November
Mid-November — abstract submission closes
Abstract review process begins
Supporting and Advancing the Athletic Training Profession through Research and Education
1

## Slide 3
ANNUAL PROCESS TIMELINE
Review Team Formation
NOVEMBER
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Preparing the Abstracts
NATA Foundation staff begin work to blind abstracts, assign codes, and group them by topical category
Abstracts are categorized into topical themes and grouped together
Reviewers are assigned as closely as possible to their area of expertise
Case studies and critically appraised topics (CATs) are spread out evenly among the 6 review groups
Review Teams
FC Chair creates the review teams
  6 teams of 2 people each; each team reviews approximately 60 abstracts
  A 7th team — FC Chair, Awards Chair, & CPC Representative — serves as the “Second Review” team for all abstracts being rejected
  This team also reviews some case studies and mechanically reviews the student exchange abstracts
Supporting and Advancing the Athletic Training Profession through Research and Education
2

## Slide 4
ANNUAL PROCESS TIMELINE
Coding & Review Website Setup
DECEMBER
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Coding & Categorization
NATA Foundation staff complete coding and create topical categories
Staff send the FC Chair a spreadsheet showing the number of abstracts submitted per category
Group Assignment
FC Chair assigns abstracts to review groups
FC Chair returns the “Reviewer Assignments Taxonomy Table” to NATA Foundation staff
Review Website
NATA Foundation staff build the review website and upload each reviewer's assigned (blinded) abstracts
Site is accessible to reviewers by early December
Supporting and Advancing the Athletic Training Profession through Research and Education
3

## Slide 5
ANNUAL PROCESS TIMELINE
Abstract Review Requirements
DECEMBER
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Review Standard
Each Peer-Review track abstract undergoes both a mechanical and a scientific merit review by at least 2 committee members
All presentations must be original work — not previously presented or published
If a manuscript is under review at submission and is later accepted prior to the meeting, the author must notify the FC Chair and the abstract is removed from the program
Eligibility & Deadlines
Previous presentation at state & district athletic training meetings, or the NATA Athletic Training Educators' Conference, is acceptable
Specific review criteria are used for original research vs. case study abstracts (full detail in Appendix A)
Reviews are completed by early January
Supporting and Advancing the Athletic Training Profession through Research and Education
4

## Slide 6
ANNUAL PROCESS TIMELINE
January Meeting: Abstract Decisions
JANUARY
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
FC Chair reviews the abstract review process with the committee; the group reviews common rejection criteria and reasons for mechanical rejection.
A Accept
R Reject
RM Reject – Mechanical
Decision Workflow
Review teams divide up and make a decision on each abstract in their group, marking it A, R, or RM; the decision is recorded in the master spreadsheet
Comments and reasons for rejection are recorded by reviewers
The “Second Review” team receives all R and RM abstracts and comments and makes the final rejection decision
This team also verifies that any NATA Foundation–funded abstract has been accepted, or identifies what minor corrections are needed for acceptance
Supporting and Advancing the Athletic Training Profession through Research and Education
5

## Slide 7
ANNUAL PROCESS TIMELINE
January Meeting: Student Award Finalists
JANUARY
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Pre-Professional/Professional Student
Post-Professional Advanced Clinical Track Student
Post-Professional Academic Doctoral Student
Selection Process
From each review group, the abstracts with the highest scores in each submission category are forwarded to the Awards Chair
Research Committee Awards Chair + at least 1 FC member select the finalists for each category
  Pre-Professional/Professional Student
  Post-Professional Advanced Clinical Track Student
  Post-Professional Academic Doctoral Student
  Early-Career
  Established Career
Award finalists will give an oral presentation of their work during the annual meeting program
Supporting and Advancing the Athletic Training Profession through Research and Education
6

## Slide 8
ANNUAL PROCESS TIMELINE
January Meeting: Program Schedule
JANUARY
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Oral Sessions
4–6 abstracts
General Poster
All week; alphabetical
Scheduling Notes
Topical clusters are created from accepted abstracts
Undergraduate students can present in any format
NATA Meetings Group determines the number of oral and poster sessions available
Final step: unblind abstracts to confirm authors are available at the times given, accounting for other scheduled presentations or moderating duties
Supporting and Advancing the Athletic Training Profession through Research and Education
7

## Slide 9
ANNUAL PROCESS TIMELINE
Moderators & Post-Meeting Wrap-Up
JANUARY
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Moderators
Generate at least 2 potential moderators for each session
Confirm moderator availability against the session schedule (CPC Representative)
Schedule oral and thematic poster sessions into rooms (CPC Representative)
Supporting and Advancing the Athletic Training Profession through Research and Education
8

## Slide 10
ANNUAL PROCESS TIMELINE
Notifications & Final Program
FEB – MAY
Setup & Submission
Review Assignment
Committee Review
Meeting Decisions
Notification
Mid-Feb
Rejection letters sent
Early
Mar
General acceptance letters sent
Early
Apr
Final letters with date & time sent
Early
May
Moderators confirmed & contacted
Mid-
May
Final info due to NATA Meetings
Thanks for your interest in the NATA Foundation Free Communications Program!
natafoundation.org/request-funding
Supporting and Advancing the Athletic Training Profession through Research and Education
9